**NH-CR 0014(185)229/COP Utilities**

**Euclid Avenue Reconstruction**

**Weekly Contractor Meeting Agenda – 6/25/2025**

**AGC Building**

**300 E. Capitol AVE**

**Pierre SD, 57501**

**Prior Week Review**

1. Work Review:
* Completed Tasks:
	+ Phase 1B
		- Concrete installed
		- Water main tested and passed
		- Fed Bldg compete with sidewalk
	+ Phase 2A
		- Gravel Install
	+ Phase 2B
		- Storm drain installed
1. Traffic Control Review:
* Phase 1B
* Phase 2A/2B
1. Safety Review:
* Safety Concerns**?**
1. Two Week Look Ahead2 Week Schedule:
* Phase 1B
	+ Switch to phase 1C Saturday June 28th
	+ Completion of storm drain
	+ Electrical installation
		- Muth Update
	+ Gravel installation
* Phase 2A
	+ Gravel installation
	+ Concrete forming
	+ Electrical
1. Subcontractor:
* Muth- Sioux Ave
* Capitol Concrete
1. Utility Relocation:
* Updates from COP
* Any other updates
1. Possible Issues Discuss: Opening of Sioux Ave
2. Utility Interruptions Planned: None
3. Traffic Control:
* Phase switch coming up from 1B to 1C
* Phase switch to open Sioux Ave

**SAFETY:**

**QUESTIONS/COMMENTS:**