**NH-CR 0014(185)229/COP Utilities**

**Euclid Avenue Reconstruction**

**Weekly Contractor Meeting Agenda – 7/23/2025**

**AGC Building**

**300 E. Capitol AVE**

**Pierre SD, 57501**

**Prior Week Review**

1. Work Review:

* Completed Tasks:
  + Phase 1B
    - Signals installed
    - Gravel installed/graded
  + Phase 2A
    - Gravel Install
    - Curb poured
  + Phase 2B
    - Utilities are installed

1. Traffic Control Review:

* Phase 1B
* Phase 2A/2B

1. Safety Review:

* Safety Concerns**?**

1. Two Week Look Ahead2 Week Schedule:

* Phase 1B
  + Muth
    - Signals and ped buttons active July 28
  + Capitol Concrete
    - Concrete for ped buttons
    - Curb and gutter form/install
* Phase 2A
  + Morris
    - Asphalt paving through Capitol 7/25,26 and 28th
    - Close Capitol 7/24
    - Open prospect 7/24
    - Open Capitol and close Prospect 7/29
  + Terratech
    - Back on site 7/29 move utility N. of Prospect
  + Muth
    - Schedule
  + Capitol Concrete
    - Working on 1B and 2A

1. Possible Issues Discuss:
2. Utility Interruptions Planned: None
3. Traffic Control:

* Capitol and Prospect opening and closing
* Signals and Ped buttons operational next week
  + Pedestrian route to remain until sidewalk poured by Fed Bldg

**SAFETY:**

**QUESTIONS/COMMENTS:**