**NH-CR 0014(185)229/COP Utilities**

**Euclid Avenue Reconstruction**

**Weekly Contractor Meeting Agenda – 7/23/2025**

**AGC Building**

**300 E. Capitol AVE**

**Pierre SD, 57501**

**Prior Week Review**

1. Work Review:
* Completed Tasks:
	+ Phase 1B
		- Signals installed
		- Gravel installed/graded
	+ Phase 2A
		- Gravel Install
		- Curb poured
	+ Phase 2B
		- Utilities are installed
1. Traffic Control Review:
* Phase 1B
* Phase 2A/2B
1. Safety Review:
* Safety Concerns**?**
1. Two Week Look Ahead2 Week Schedule:
* Phase 1B
	+ Muth
		- Signals and ped buttons active July 28
	+ Capitol Concrete
		- Concrete for ped buttons
		- Curb and gutter form/install
* Phase 2A
	+ Morris
		- Asphalt paving through Capitol 7/25,26 and 28th
		- Close Capitol 7/24
		- Open prospect 7/24
		- Open Capitol and close Prospect 7/29
	+ Terratech
		- Back on site 7/29 move utility N. of Prospect
	+ Muth
		- Schedule
	+ Capitol Concrete
		- Working on 1B and 2A
1. Possible Issues Discuss:
2. Utility Interruptions Planned: None
3. Traffic Control:
* Capitol and Prospect opening and closing
* Signals and Ped buttons operational next week
	+ Pedestrian route to remain until sidewalk poured by Fed Bldg

**SAFETY:**

**QUESTIONS/COMMENTS:**