**NH-CR 0014(185)229/COP Utilities**

**Euclid Avenue Reconstruction**

**Weekly Contractor Meeting Agenda – 7/09/2025**

**AGC Building**

**300 E. Capitol AVE**

**Pierre SD, 57501**

**Prior Week Review**

1. Work Review:
* Completed Tasks:
	+ Phase 1B
		- Grading and Hauling off excess material
		- Temporary storm sewer connection in the alley near Walgreens
		- Made a plan for the Storm drain at Sta. 12+09
	+ Phase 1C
		- Capital Contractors poured center turning lane of Sioux Ave.
	+ Phase 2A
		- Gravel Install
		- Adjusted Manhole #5A
		- Capital Contractors forming up Sta. 18+00 to 19+07
		- Muth began conduit installations
	+ Phase 2B
		- Waterline installation completed up to Sta. 227+00
		- Water service at 225+87
1. Traffic Control Review:
* Phase 1C – Sioux Ave. intersection reopening today
* Phase 1B – Will stay as it is
* Phase 2A/2B
	+ Opening of capital Ave. East/West on travel gravel yesterday
	+ Prospect closed this morning – cul-de-sac configuration
1. Safety Review:
* Safety Concerns**?**
1. Two Week Look Ahead2 Week Schedule:
* Phase 1C
	+ Permanent traffic markings/signs being installed
	+ Muth Electric install signals as soon as they come in
	+ Opening of the Sioux Ave. intersection and South Pierre street today 7/9/25
* Phase 1B
	+ Completion of storm drain addition 12+09
	+ Electrical installation
		- Muth Update
	+ Gravel installation
	+ Beginning of concrete work
* Phase 2A
	+ Concrete work
	+ Curb & gutter
* Phase 2B
	+ Waterline Tie in at Prospect Ave.
	+ Lumen Relocation starts Monday
	+ RCP
	+ Subgrade Grading
1. Subcontractor:
* Muth- Sioux Ave
* Capitol Concrete
1. Utility Relocation:
* Updates from COP
* Any other updates
1. Possible Issues Discuss:
2. Utility Interruptions Planned: Today at noon
3. Traffic Control:
* Phase 1C – Sioux Ave. intersection reopening today
* Phase 1B – Will stay as it is
* Phase 2A/2B
	+ Opening of capital Ave. East/West on travel gravel yesterday
	+ Prospect closed this morning – cul-de-sac configuration

**SAFETY:**

**QUESTIONS/COMMENTS:**