**NH-CR 0014(185)229/COP Utilities**

**Euclid Avenue Reconstruction**

**Weekly Contractor Meeting Agenda – 7/09/2025**

**AGC Building**

**300 E. Capitol AVE**

**Pierre SD, 57501**

**Prior Week Review**

1. Work Review:

* Completed Tasks:
  + Phase 1B
    - Grading and Hauling off excess material
    - Temporary storm sewer connection in the alley near Walgreens
    - Made a plan for the Storm drain at Sta. 12+09
  + Phase 1C
    - Capital Contractors poured center turning lane of Sioux Ave.
  + Phase 2A
    - Gravel Install
    - Adjusted Manhole #5A
    - Capital Contractors forming up Sta. 18+00 to 19+07
    - Muth began conduit installations
  + Phase 2B
    - Waterline installation completed up to Sta. 227+00
    - Water service at 225+87

1. Traffic Control Review:

* Phase 1C – Sioux Ave. intersection reopening today
* Phase 1B – Will stay as it is
* Phase 2A/2B
  + Opening of capital Ave. East/West on travel gravel yesterday
  + Prospect closed this morning – cul-de-sac configuration

1. Safety Review:

* Safety Concerns**?**

1. Two Week Look Ahead2 Week Schedule:

* Phase 1C
  + Permanent traffic markings/signs being installed
  + Muth Electric install signals as soon as they come in
  + Opening of the Sioux Ave. intersection and South Pierre street today 7/9/25
* Phase 1B
  + Completion of storm drain addition 12+09
  + Electrical installation
    - Muth Update
  + Gravel installation
  + Beginning of concrete work
* Phase 2A
  + Concrete work
  + Curb & gutter
* Phase 2B
  + Waterline Tie in at Prospect Ave.
  + Lumen Relocation starts Monday
  + RCP
  + Subgrade Grading

1. Subcontractor:

* Muth- Sioux Ave
* Capitol Concrete

1. Utility Relocation:

* Updates from COP
* Any other updates

1. Possible Issues Discuss:
2. Utility Interruptions Planned: Today at noon
3. Traffic Control:

* Phase 1C – Sioux Ave. intersection reopening today
* Phase 1B – Will stay as it is
* Phase 2A/2B
  + Opening of capital Ave. East/West on travel gravel yesterday
  + Prospect closed this morning – cul-de-sac configuration

**SAFETY:**

**QUESTIONS/COMMENTS:**