NH-CR 0014(185)229/COP Utilities

Euclid Avenue Reconstruction

Weekly Contractor Meeting Agenda – 8/27/2025

AGC Building

300 E. Capitol AVE

Pierre SD, 57501

Prior Week Review

- Work Review:

- Completed Tasks:

  - Phase 1D

    - Sanitary bypass running

    - Surfacing Removal

  - Phase 2A

    - Sidewalks completed

  - Phase 2B

    - Undercut and gravel

- Traffic Control Review:

- All Phase

- Safety Review:

- Safety Concerns?

- Two Week Look Ahead 2 Week Schedule:

- Phase 1D

  - Finish Sanitary sewer the 29th

  - Start Storm Drain

  - Traffic control switch to Phase D2 9/3

    - Moved up from 9/15

- Phase 2A

  - Fillets

  - East side of sidewalk and approach open

  - Electrical

    - Muth Luminaires

    - Lighting on Capitol

- Phase 2B

  - Curb and Gutter 9/27

  - Fillets 9/29

  - Sidewalk

  - Muth

          - Update

        - Phase 2C

          - Utility Relocation

          - Storm drain

- Utility Relocation:

- Updates from COP/Terratech

- Any other updates

- Possible Issues Discuss:

- Night monitor for Sewer Bypass

- Traffic Control:

SAFETY:

Reminder- Keep safety as top priority. This includes housekeeping, safe equipment operation and making sure pedestrians have a safe route.

QUESTIONS/COMMENTS: