**NH-CR 0014(185)229/COP Utilities**

**Euclid Avenue Reconstruction**

**Weekly Contractor Meeting Agenda – 8/27/2025**

**AGC Building**

**300 E. Capitol AVE**

**Pierre SD, 57501**

**Prior Week Review**

* Work Review:
* Completed Tasks:
  + Phase 1D
    - Sanitary bypass running
    - Surfacing Removal
  + Phase 2A
    - Sidewalks completed
  + Phase 2B
    - Undercut and gravel
* Traffic Control Review:
* All Phase
* Safety Review:
* Safety Concerns**?**
* Two Week Look Ahead2 Week Schedule:
* Phase 1D
  + Finish Sanitary sewer the 29th
  + Start Storm Drain
  + Traffic control switch to Phase D2 9/3
    - Moved up from 9/15
* Phase 2A
  + Fillets
  + East side of sidewalk and approach open
  + Electrical
    - Muth Luminaires
    - Lighting on Capitol
* Phase 2B
  + Curb and Gutter 9/27
  + Fillets 9/29
  + Sidewalk
  + Muth

Update

* + - * + Phase 2C

Utility Relocation

Storm drain

* Utility Relocation:
* Updates from COP/Terratech
* Any other updates
* Possible Issues Discuss:
* Night monitor for Sewer Bypass
* Traffic Control:

**SAFETY:**

Reminder- Keep safety as top priority. This includes housekeeping, safe equipment operation and making sure pedestrians have a safe route.

**QUESTIONS/COMMENTS:**