**NH-CR 0014(185)229/COP Utilities**

**Euclid Avenue Reconstruction**

**Weekly Contractor Meeting Agenda – 9/17/2025**

**AGC Building**

**300 E. Capitol AVE**

**Pierre SD, 57501**

**Prior Week Review**

* Work Review:
* Completed Tasks:
  + Phase 1D
    - Storm Drain
    - Water main/service
  + Phase 2B
  + Phase 2C
    - Undercut
    - Storm Drain Laterals
* Wynoka
  + Trees removed
  + Sprinklers blown out and surveyed
  + Pipe install
* Traffic Control Review:
* All Phase
* Safety Review:
* Safety Concerns**?**
* Two Week Look Ahead2 Week Schedule:
* Phase 1D/E
  + Water completed by 9/24
  + Storm drain completed by 10/03
  + Water service and sanitary service to The Crossing
* Phase 2B
  + Electrical
  + Asphalt paving 9/24
    - * + Phase 2C

Utility Relocation

Asphalt Paving 9/24

* Utility Relocation:
* Updates from COP/Terratech
* Any other updates
* Wynoka
  + Set junction box
  + Aware how much pipe will be visible?
* Traffic Control
  + Muth to update pedestrian heads night of the 17th
* Possible Issues, Discuss:
  + Weather

**SAFETY:**

Reminder- Keep safety as top priority. This includes housekeeping, safe equipment operation and making sure pedestrians have a safe route.

**QUESTIONS/COMMENTS:**