NH-CR 0014(185)229/COP Utilities

Euclid Avenue Reconstruction

Weekly Contractor Meeting Agenda – 9/17/2025

AGC Building

300 E. Capitol AVE

Pierre SD, 57501

Prior Week Review

- Work Review:

- Completed Tasks:

  - Phase 1D

    - Storm Drain

    - Water main/service

  - Phase 2B

  - Phase 2C

    - Undercut

    - Storm Drain Laterals

- Wynoka

  - Trees removed

  - Sprinklers blown out and surveyed

  - Pipe install

- Traffic Control Review:

- All Phase

- Safety Review:

- Safety Concerns?

- Two Week Look Ahead 2 Week Schedule:

- Phase 1D/E

  - Water completed by 9/24

  - Storm drain completed by 10/03

  - Water service and sanitary service to The Crossing

- Phase 2B

  - Electrical

  - Asphalt paving 9/24

        - Phase 2C

          - Utility Relocation

          - Asphalt Paving 9/24

- Utility Relocation:

- Updates from COP/Terratech

- Any other updates

- Wynoka

  - Set junction box

  - Aware how much pipe will be visible?

- Traffic Control

  - Muth to update pedestrian heads night of the 17th

- Possible Issues, Discuss:

  - Weather

SAFETY:

Reminder- Keep safety as top priority. This includes housekeeping, safe equipment operation and making sure pedestrians have a safe route.

QUESTIONS/COMMENTS: