NH-CR 0014(185)229/COP Utilities

Euclid Avenue Reconstruction

Weekly Contractor Meeting Agenda – 9/10/2025

AGC Building

300 E. Capitol AVE

Pierre SD, 57501

Prior Week Review

- Work Review:

- Completed Tasks:

  - Phase 1D

    - Sanitary complete

    - Water to Pleasant

  - Phase 2B

    - Sidewalks and fillets

  - Phase 2C

    - Storm drain to Broadway

- Traffic Control Review:

- All Phase

- Safety Review:

- Safety Concerns?

- Two Week Look Ahead 2 Week Schedule:

- Phase 1D/E

  - Water line install from Euclid to Rowan Tree scheduled to be completed by 9/12

  - Storm drain install to pleasant intersection

  - Water service and sanitary service to The Crossing

- Phase 2B

  - Sidewalk

  - Electrical

        - Phase 2C

          - Utility Relocation

          - Storm drain

- Utility Relocation:

- Updates from COP/Terratech

- Any other updates

- Possible Issues Discuss:

  - Electrical

  - Additional work/storm drain

- Traffic Control:

SAFETY:

Reminder- Keep safety as top priority. This includes housekeeping, safe equipment operation and making sure pedestrians have a safe route.

QUESTIONS/COMMENTS: