NH-CR 0014(185)229/COP Utilities

Euclid Avenue Reconstruction

Weekly Contractor Meeting Agenda – 10/01/2025

AGC Building

300 E. Capitol AVE

Pierre SD, 57501

Prior Week Review

- Work Review:

- Completed Tasks:

  - Phase 1D

    - Storm Drain to Pleasant

    - Water and sewer connections

  - Phase 2B/C

    - Signals

    - Asphalt

- Wynoka

  - Utility lowered

  - Junction installed

- Traffic Control Review:

- All Phase

- Safety Review:

- Safety Concerns?

- Two Week Look Ahead 2 Week Schedule:

- Phase 1D/E

  - Storm drain in Pleasant Ave installed by 10/03

  - Storm drain from intersection to Music Store

  - Begin undercut

        - Phase 2B/C/D

          - Traffic Markings

          - Cleanup/landscape work

- Utility Relocation:

- MDU

- Wynoka

  - Continue RCP installation

  - Sidewalk replacement

- Traffic Control

  - Signals are up at Capitol

  - Markings planned for 10/06 from Pleasant to Prospect

- Possible Issues, Discuss:

SAFETY:

Reminder- Keep safety as top priority. This includes housekeeping, safe equipment operation and making sure pedestrians have a safe route.

QUESTIONS/COMMENTS: