NH-CR 0014(185)229/COP Utilities

Euclid Avenue Reconstruction

Weekly Contractor Meeting Agenda – 10/06/2025

AGC Building

300 E. Capitol AVE

Pierre SD, 57501

Prior Week Review

- Work Review:

- Completed Tasks:

  - Phase 1D

    - Undercut

  - Phase 2B/C

    - Signals

    - Traffic Markings

- Wynoka

  - Set 3rd Junction Box

- Traffic Control Review:

- All Phase

- Safety Review:

- Safety Concerns?

- Two Week Look Ahead 2 Week Schedule:

- Phase 1D/E

  - Finish undercut

  - Sidewalk Removals/grading

  - Storm drain to Music Store

        - Phase 2B/C/D

          - Replace Manhole

          - Storm drain laterals

          - Undercut/grading

          - Curb and gutter

- Utility Relocation:

- Wynoka

  - Place topsoil and prep for sidewalk replacement

- Traffic Control

  - Open Pleasant to Euclid

- Possible Issues, Discuss:

SAFETY:

Reminder- Keep safety as top priority. This includes housekeeping, safe equipment operation and making sure pedestrians have a safe route.

QUESTIONS/COMMENTS: