NH-CR 0014(185)229/COP Utilities

Euclid Avenue Reconstruction

Weekly Contractor Meeting Agenda – 10/22/2025

AGC Building

300 E. Capitol AVE

Pierre SD, 57501

Prior Week Review

- Work Review:

- Completed Tasks:

  - Phase 1D

    - CMP/RCP

  - Phase 2B/C

    - Curb and gutter

- Wynoka

  - 2 sidewalks poured back

- Traffic Control Review:

- All Phase

- Safety Review:

- Safety Concerns?

- Two Week Look Ahead 2 Week Schedule:

- Phase 1D/E

  - Complete storm sewer to music store

  - Install gravel

  - Curb and gutter

  - Mainline paving

        - Phase 2B/C/D

          - Gravel installation

          - Curb and gutter

          - Asphalt paving

- Utility Relocation:

- NA

- Wynoka

  - On hold until gravel installation is completed

- Traffic Control

- Possible Issues, Discuss:

  - Weather limitations for asphalt paving

SAFETY:

Reminder- Keep safety as top priority. This includes housekeeping, safe equipment operation and making sure pedestrians have a safe route.

QUESTIONS/COMMENTS: