NH-CR 0014(185)229/COP Utilities

Euclid Avenue Reconstruction

Weekly Contractor Meeting Agenda – 11/05/2025

AGC Building

300 E. Capitol AVE

Pierre SD, 57501

Prior Week Review

- Work Review:

- Completed Tasks:

  - Asphalt complete for season

  - Undercut and gravel install on Pleasant

  - Curb installed by bridge

  - Lower portion of Gulch stabilized

- Traffic Control Review:

- All Phase

- Safety Review:

- Safety Concerns?

- Two Week Look Ahead 2 Week Schedule:

- Phase 1D/E

  - Mainline concrete pour

    - Pour schedule: complete from bridge to corner by 11/12

    - Form Pleasant

  - Sidewalk/apron grading

  - Muth- Base installation

        - Phase 2B/C/D

          - Permanent markings

          - Muth-Base installation and set poles

            - 12th and 13th drill and pour

            - 17th Hoffman on site to hang poles

            - 24th startup/open Wynoka to Pleasant

- Utility Relocation:

- NA

- Wynoka

  - Set box and tie in

  - Week of the 10th backfill, shape

  - Week of the 17th sidewalk and stabilize

- Traffic Control

  - Communication with business owners as driveways open and close

  - Opening of Wynoka to Pleasant

- Possible Issues, Discuss:

  - Weather limitations for asphalt paving

SAFETY:

Reminder- Keep safety as top priority. This includes housekeeping, safe equipment operation and making sure pedestrians have a safe route.

QUESTIONS/COMMENTS: